## 1. Product Overview
Item | Description
Product Name | SummAID
Product Vision/ Purpose | An on-premise AI platform that synthesizes fragmented patient medical reports (radiology, pathology, labs) into a single, verifiable pre-visit summary.
Business Goals / Key Success factors | To reduce clinician burnout and patient safety risks by delivering a 100% on-premise (Security) , "Glass Box" verifiable (Trust) , and synthesized (Insight) AI summary.
Primary Stakeholders | The Medical Assistant/Nurse (Primary User), the Doctor (Beneficiary) , and the Hospital IT/Admin (Buyer).

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Live Generation and RAG | US1 | As a Medical Assistant (MA), I want to click a "Generate Summary" button for a patient to trigger the live RAG process. | React (Vite) frontend | Must Have | 2 | Done | Frontend Dev | 1. Load the "Fake EMR" patient list page. 2. Verify a "Generate Summary" button is visible for "Patient-001". 3. Click the button. 4. Open browser dev tools (Network tab) and confirm a request is sent to the correct FastAPI endpoint. | QA / Frontend Dev
|  | US2 | As a developer, when a request is received, I need the system to perform a "Hybrid Search" to find the most relevant context. | • FastAPI endpoint to receive the request. • Python psycopg2 or sqlalchemy to connect to PostgreSQL. • SQL query using pgvector operator (e.g., <=>). • SQL query using LIKE or ILIKE. • A "fusion" algorithm (e.g., Reciprocal Rank Fusion) to combine search results. • LangChain (Python) orchestration. | Must Have | 8 | Done | Backend Dev | 1. Send a test request (e.g., via Postman) to the summary endpoint with a patient_id. 2. Check the application logs to confirm three separate SQL queries (vector, keyword, metadata) were executed. 3. Verify the "fused" context (the output of this step) contains text from the relevant reports. | Backend Dev
|  | US3 | As a developer, I need the backend to send the fused context to the local LLM and return the final summary to the user. | • Python httpx or requests library to make an API call to the local Ollama instance (e.g., http://localhost:11434/api/generate). • A well-formed prompt template (system prompt + user prompt with fused context). • LangChain (Python) to manage the LLM call. | Must Have | 5 | Done | Backend Dev | 1. Using a mocked "fused context" as input, call the generation function. 2. Confirm that an API call is made to the Ollama llama3:8b endpoint. 3. Confirm that the (mocked or real) text response from Ollama is captured. 4. Confirm this text is included in the final JSON response from the FastAPI endpoint. | Backend Dev
E2 | "Glass Box" Verification | US4 | As a Medical Assistant (MA), I want to see a citable summary in the UI so I can trust the output. | • Backend must send the summary with citation markers and source data (e.g., {"summary": "...", "citations": [{"id": 1, "source_pdf": "report.pdf", ...}]}). • React UI state (e.g., useState) to store the summary and citation data. • React component to parse and render the summary, turning [1] into a clickable <button>. | Must Have | 3 | Done | Frontend Dev | 1. Trigger a summary generation. 2. When the summary text appears, verify that any citation markers (e.g., [1]) are rendered as clickable links or buttons. 3. Verify the summary text without citations also renders correctly. | QA / Frontend Dev
|  | US5 | As an MA, when I click a citation, I want to see the exact source of the information in the original document. | • React onClick handler for the citation link. • A method to serve the static PDF files (e.g., from the React public folder). • A PDF rendering library in React (e.g., react-pdf). • Logic to pass the "source sentence" or coordinates to the PDF viewer to highlight text. | Must Have | 8 | Done | Frontend Dev | 1. Get a summary with a citation [1]. 2. Click [1]. 3. Verify that a new view/modal opens, loading the correct source PDF (e.g., pathology_report.pdf). 4. Verify that the specific source sentence (e.g., "The tumor is malignant") is highlighted or scrolled into view. | QA
E3 | Manual Data Seeding | US6 | As a Developer, I need a manual script to parse and extract text from all sample PDFs. | • Python 3.x • PyMuPDF (fitz) library. • pytesseract and Pillow (PIL) libraries. • A local Tesseract OCR engine installation. • File system operations (os.listdir). | Must Have | 5 | Done | Backend Dev | 1. Place one text-based PDF and one image-based (scanned) PDF in the ./sample_reports folder. 2. Run python seed.py. 3. Verify the script outputs the extracted text for the text-PDF (using PyMuPDF). 4. Verify the script outputs the extracted text for the scanned-PDF (using Tesseract). | Backend Dev
|  | US7 | As a Developer, I need the seed script to create and store embeddings for the extracted text. | • Python httpx or requests to call the Ollama embedding endpoint. • Text chunking logic (e.g., RecursiveCharacterTextSplitter). • psycopg2 or sqlalchemy. • SQL INSERT statement for a table with a vector(768) column type (from pgvector). | Must Have | 5 | Done | Backend Dev | 1. Run the seed.py script with a sample PDF. 2. Connect to the PostgreSQL Docker container (e.g., using psql or DBeaver). 3. SELECT * FROM your_table; 4. Verify that the vector column is populated with a 768-dimension vector and is not NULL. | Backend Dev
|  | US8 | As a Developer, I need the seed script to encrypt and store the raw text in the database. | • Python dotenv library to read .env file. • psycopg2 or sqlalchemy. • SQL INSERT statement using PGP_SYM_ENCRYPT(text, key). • RAG pipeline (US-002) must be updated to use PGP_SYM_DECRYPT. | Must Have | 3 | Done | Backend Dev | 1. Run seed.py with a sample PDF containing the text "Patient is healthy". 2. Connect to the PostgreSQL DB. 3. SELECT encrypted_text_column FROM your_table; 4. Verify the result is not "Patient is healthy" but is a block of binary/armored text. | Backend Dev
E4 | Demo Infrastructure | US9 | As a Developer, I need to set up a single-node PostgreSQL database for the demo. | • docker-compose.yml file. • A PostgreSQL Docker image (e.g., postgres:16 or ankane/pgvector). • An initialization script (.sql file) to run on startup that executes CREATE EXTENSION.... | Must Have | 3 | In Progress | DevOps / Backend Dev | 1. Run docker-compose up. 2. Connect to the running container using psql. 3. Run \dx command. 4. Verify pgcrypto and vector are both listed as installed extensions. | DevOps / Backend Dev
|  | US10 | As a Developer, I need to set up the local AI models for the demo. | • Ollama installed on the host machine or a docker-compose.yml entry for ollama/ollama. • A startup script or docker exec commands to run ollama pull llama3:8b and ollama pull nomic-embed-text. | Must Have | 2 | Done | DevOps / Backend Dev | 1. Start the Ollama service/container. 2. Run ollama list. 3. Verify that llama3:8b and nomic-embed-text appear in the list of available models. | DevOps / Backend Dev
E5 | Specialized Clinical Modules | US11 | As an Audiologist, I want the AI to extract dB levels/frequencies from Audiogram images to track hearing loss trends. | • Multimodal AI (e.g., Llama 3.2 Vision or OCR specific to charts) • Logic to map X/Y coordinates to Hz/dB values • Time-series graphing library (e.g., Recharts) | Should Have | 13 | In Progress | AI / Backend | 1. Upload Audiogram image. 2. Verify JSON output contains correct Hz/dB pairs. 3. Verify trend graph renders correctly in UI. | AI Lead
E6 | Advanced AI Architecture | US12 | As a Backend Dev, I want a "Prompt Router" to switch system prompts based on report type (Speech vs. Oncology). | • Classification logic (Keyword or Zero-shot) • Prompt Registry (YAML/JSON) • Dynamic Prompt Injection in LangChain | Must Have | 5 | Done | Backend Dev | 1. Ingest "Oncology Report". 2. Verify logs show "Oncology System Prompt" was selected. 3. Verify output uses oncology-specific terminology. | Backend Dev
|  | US13 | As a Backend Dev, I want to implement the Dual-Model logic (Llama3 for text + Nomic for vectors) in the pipeline. | • LangChain configuration for split-pipeline • Docker resource allocation (ensure both fit in RAM) • Async embedding generation | Must Have | 5 | Done | Backend Dev | 1. Send text to pipeline. 2. Confirm embedding uses Nomic (768 dims). 3. Confirm generation uses Llama3. | Backend Dev
E7 | Clinical Workflow Suite | U14 | As a Doctor, I want a "Digital Rx Writer" with auto-complete so I can prescribe quickly within the summary view. | • Drug Name Database (Local seed or API) • React Autocomplete component • "Prescription" Table in DB | Should Have | 8 | Done | Frontend Dev | 1. Type "Amox" in Rx bar. 2. Verify "Amoxicillin" appears. 3. Select and Save. 4. Verify Rx is saved to patient record. | QA
|  | U15 | As a Doctor, I want an automated "Allergy Safety Check" to warn me if a prescribed drug conflicts with patient history. | • Logic to compare Rx vs. "Allergies" list in DB • Fuzzy matching (e.g., "Penicillin" matches "Penicillins") • UI Warning Modal | Should Have | 8 | Done | Backend Dev | 1. Patient has "Sulfa" allergy. 2. Prescribe "Bactrim". 3. Verify "Safety Warning" modal appears immediately. | QA
|  | U16 | As a Doctor, I want to highlight summary text to add a "Clinical Annotation" for future context. | • Text Selection API (Frontend) • DB Schema: Annotation (linked to summary_id and text range) • UI Tooltip for existing notes | Should Have | 5 | Done | Frontend Dev | 1. Highlight sentence in summary. 2. Click "Annotate" and type note. 3. Refresh page. 4. Hover over text to see note. | QA
E8 | Interactive Intelligence | U17 | As a Doctor, I want an Interactive Chatbot to ask specific Q&A against the patient's history. | • Chat UI Component • Conversational Memory (Redis/Postgres) • RAG Pipeline w/ Follow-up capabilities | Must Have | 13 | Done | Full Stack | 1. Ask "When was the last MRI?". 2. Verify answer is correct based on reports. 3. Ask "What was the result?". 4. Verify context is maintained. | AI Lead

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-21 | E-001: Core RAG Pipeline (Live JIT) E-002: "Glass Box" Verification (Citations) E-003: Manual Data Seeding (Script) E-004: Demo Infrastructure (Single Node) E-005: Specialized Clinical Modules E-006: Advanced AI Architecture E-007 Clinical Workflow Suite E-008: Interactive Intelligence | Sample Data: Access to 10-20 anonymized PDF medical reports (Radiology, Pathology, etc.) to test the extraction logic. Local Hardware: A developer laptop with sufficient RAM (likely 16GB+) to run Docker and the local LLM (llama3:8b) simultaneously. Model Availability: Ability to download/pull llama3:8b and nomic-embed-text from Ollama. | On Track
v0.2 | 2025-12-07 | E-009: Resilient Ingestion (RabbitMQ Cluster) E-010: Asynchronous Workflow (Nightly Batch) E-011: Enterprise Security (Vault & No .env) E-012: HA Infrastructure (Patroni & Load Balancers) E-013: Compliance (mTLS, Audit Logs, Erasure) | Phase 1 Success: The demo must successfully prove technical feasibility to get the "green light". Hospital Buy-In: Approval from the CISO/CIO to provision on-premise resources. Server Hardware: Procurement of on-premise servers with GPUs to run the "Multiple Ollama Replicas" and worker pools. Infrastructure Stack: Availability of a Kubernetes environment to host the HA clusters (RabbitMQ, Vault, Patroni). | Planned
v0.3 | 2025-12-20 | E-014: Live EMR Integration (HL7/FHIR feeds) E-015: Doctor Feedback Loop (Reinforcement Learning) E-016: Multi-Department Support (Oncology, Cardiology) | Pilot Success: Positive feedback from the doctors/MAs during the Phase 2 pilot. Live Access: Permission and network credentials to connect directly to the hospital's live EMR database or HL7 feed (moving beyond PDF drops). Regulatory Sign-off: Final compliance review for handling real-time patient data at scale. | Planned

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Setting up the local Ollama instance with llama3:8b was very fast | Tesseract OCR is much slower than expected for scanned PDFs . | Research faster OCR settings or resize images before processing | Backend Dev
The pgvector extension works perfectly for similarity search. | The manual seed.py script crashes on large files | Add error handling to the seed script so it skips bad files | Backend Dev
The "Glass Box" citation links are working correctly in the UI. | The AI sometimes hallucinates facts if the retrieved context is too short. | Tune the chunk size in the RAG pipeline to capture more context | AI Lead
React frontend is very responsive. | PDF table data is getting scrambled during extraction. | Improve table parsing logic in PyMuPDF | Backend Dev
The AI Model has small context window so the summary is not that good